## Sheet1
Prosperity Connection Board Work Plan '25-'26 |  | 2025 | [11 empty] | 2026
2025-03-14 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Committees | ANNUAL MEETING | Committees | Full Board | Committees | Full Board | Committees | Full Board | Committees | Full Board | Committees | Full Board | Committees | ANNUAL MEETING | Committees | Full Board | Committees | Full Board | Committees | Full Board | Committees | Full Board | Committees | Full Board
Task | Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Board & Organizational Planning
Review & Approve 2-year Work Plan | Full Board | bar: Apr
Review Current PC Strategic Plan | Full Board | bar: Jul; Dec; Jul; Dec
Begn Plans for next PC 3-year Strategic Plan | All Committees/Full Board | bar: Apr to Jul
Review & Approve next PC Strategic Plan | All Committees/Full Board | bar: Sep to Dec
Review Progress of Board Work Plan | Full Board | bar: Aug; Feb; Aug
Draft '27-'28 Board Work Plan | All Committees/Full Board | bar: Sep to Dec
Assess Board Performance | Governance/Full Board | bar: Mar to Apr; Mar to Apr
Governance
Review bylaws | Governance | bar: Jan
Review succession plan/committee membership | Governance | bar: Jan; Mar; Jul; Jan; Mar; Jul
Present slate to Full Board | Governance | bar: Sep; Sep
Vote on slate of Officers | Full Board | [24 empty] | (December meeting only if more time needed to review) | bar: Oct; Dec; Oct; Dec
Board education | Full Board | bar: Aug; Aug
Review major risks facing the organization | All Committees/Full Board | bar: Mar to Apr; Sep to Oct; Mar to Apr; Sep to Oct
Internal
Audit
Hire auditor & manage audit | Internal | bar: Jan to Mar; Nov to Mar; Nov to Dec
Review and approve audit | Full Board | bar: Apr; Apr
Budget
Midyear Budget Review/Funding Forecast | Internal | bar: Jul; Sep; Jul; Sep
Financial Reports | Internal/Full Board | bar: Jan to Dec
Oversee Annual Budget Prep | Internal | bar: Sep; Nov; Sep; Nov
Review Draft Annual Budget | Full Board | bar: Oct; Oct
Approve Annual Budget | Full Board | bar: Dec; Dec
HR
Review/Develop/Update Employee Handbook | Internal | bar: Sep; Sep
Approve Employee Handbook | Full Board | bar: Oct; Oct
Review PEO Provider | Internal | bar: Sep; Sep
Add committee members as needed | Internal | bar: Jan; Jul; Jan; Jul
External
Add committee members as needed | External | bar: Mar; Sep; Mar; Sep
Review funding diversification plan | Internal/External | bar: May; May
Review marketing outcomes | External | bar: Jan; Mar; May; Jul; Sep; Nov; Jan; Mar; May; Jul; Sep; Nov
Personnel
Review performance goals for Executive Dir. | Governance | bar: Jul; Jul
ED Performance Appraisal | Governance/Full Board | bar: Nov to Dec; Nov to Dec
ED Succession Planning/C-Suite Review | Governance/Full Board | bar: Mar; Mar